## Sheet1
Priority | Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Day 1 | Day 2 | Day 3 | Day 4
1 | Jacob Baker | Implment Edit Account Portfolio Page | 2 | 2 | 0 | 0 | 0
1 | Jacob Baker | Bind Projects to account/user data | 2 | 2 | 1 | 0 | 0
1 | Jacob Baker | Bind Edits to UI and Update Account Portfolio Page | 2 | 2 | 1 | 0 | 0
2 | Jacob Baker | Implments login feature | 2 | 2 | 0 | 0 | 0
2 | Jacob Baker | Implment sign out feature | 1 | 1 | 0 | 0 | 0
2 | Jacob Baker | Implments create account feature | 2 | 2 | 0 | 0 | 0
1 | Jacob Baker | Create Website and bind hosting | 3 | 1 | 1 | 1 | 0
1 | Jacob Baker | Deploy website | 2 | 2 | 2 | 2 | 0
|  | Estimate Totals | 16 | 14 | 5 | 3 | 0
| Task Manager / Dev | Task Description | Hours Worked
|  | Implmented create account | 2
|  | implmented sign in and logout | 0.5
|  | implmented editing Account page | 3.5
|  | Refactored Project Page | 2
|  | Binded Projects and Account Pages together | 3
|  | Fixed small bugs for the Account and project page | 4
|  | Tested all of the system past 95% code coverage. | 2
|  | Finished Java code for this sprint | 3
|  | Created Website and bined project dowload | 4
|  | Binded hosting | 2
|  | Deployed Website | 3
|  | Created a set Up script to run through program | 4
|  | Estimate Totals | 33