## Sheet1
Priority | Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2
1 | Jacob Baker | Initalize Project | 0.5 | 0
2 | Jacob Baker | Implment UI Login and Create Account | 1 | 1
1 | Jacob Baker | Implment UI Home Screen | 1 | 0
1 | Jacob Baker | Implment Account Portfolio Page | 1 | 0
1 | Jacob Baker | Implment Project Details page | 2 | 0
2 | Jacob Baker | Implment Result Page | 2 | 2
1 | Jacob Baker | Bind Page flow | 1.5 | 0
2 | Jacob Baker | Implment Edit Account Portfolio Page | 2 | 1
1 | Jacob Baker | Implment Edit Project Page | 2 | 0
1 | Jacob Baker | Bind Edits to UI and Update Account Portfolio Page | 1 | 1
1 | Jacob Baker | Bind Edits to UI and Update Project Pages | 1 | 0
|  | Estimate Totals | 15 | 5 | 0
| Task Manager / Dev | Task Description | Hours Worked
| Jacob Baker | Initalized the project with working code | 0.5
| Jacob Baker | Implemented the UI for the Home Screen | 1.5
| Jacob Baker | Implemented the UI for the Account Portfolio | 1.5
| Jacob Baker | Implemented the UI for the Project Page | 2
| Jacob Baker | Binded the Pages to flow with GuiHelper | 1
| Jacob Baker | Implmented file upload for the projects | 2.5
| Jacob Baker | Implmented rest of the Project page View UI and Binding | 2.5
|  | Estimate Totals | 11.5